## CAP
Category | Capability | Observation | Recommendation | Corrective Action | Capability Element | Primary Responsible Agency | Agency Point of Contact | Start Date | Completion Date
Common Capabilities
| 1. Communication | Information flow from residents via ICP and DOC to EOC not tested REMOVE SECTION? | 1.1 Implement process for sit stat reporting to EOC | 1.1.1 Develop concept for collecting, summarizing and transmitting sit stat information from residents | Planning
|  |  |  | 1.1.2 Drill the information flow from residents via ICP and DOC to EOC | Exercises
|  | Limited use of communication capability at ICP REMOVE SECTION? | 1.3 Educate CERT, DART and MRC staff about CARES capabilities | 1.3.1 Training for CERT, DART and MRC staff | Training
|  |  |  | 1.3.2 Tabletop on message drafting and handling | Exercises
|  |  |  | 1.3.3 Joint communication drill with CERT, DART, MRC and CARES | Exercises
|  | No electronic communication link between DOC and Comm Van | 1.4 Set up WiFi access point with high gain antenna mounted on roof of Comm Van | 1.4.1 Procure equipment | Equipment
|  |  |  | 1.4.2 Drill communication between DOC and Comm Van, using WiFi and Outpost Messenger | Exercises
| 2. Community Preparedness and Participation | Declining participation, esp in CERT | 2.1 Develop and implement plan to increase membership and engagement | 2.1.1 Investigate reasons for declining participation | Personnel
|  |  |  | 2.1.2 Establish program to re-engage and motivate CERT trained volunteers | Personnel
|  |  |  | 2.1.3 Develop concept how to best utilize volunteers qualfied for several CCC branches | Personnel
|  | Concept of supervision (as required by Emergency Services Act) not implemented in CCC | 2.2 Implement role of supervisors within the CCC organization | 2.2.1 Define training requirements | Training
|  |  |  | 2.2.2 Implement training | Training
|  |  |  | 2.2.3 Mainting list of CCC volunteers qualified for supervisory tasks | Training
|  | Limited understanding of bigger picture (how CCC is embedded in overall disaster response) | 2.3 Implement training program going beyond core CCC capabilities | 2.3.1 Develop and offer training for - disaster management - EOC and DOC management - exercise planning | Training
Respond Mission Capabilities
| 3. Onsite Incident Management | Opening the mobile ICP took much time | 3.1 Drop the concept of proctors at the drill and have the senior staff as active ICP participants and train by example | 3.1.1 Mini-drills to practice ARK opening with experienced staff. | Exercises
|  | Assignment of volunteers to teams time consuming | 3.2 This was caused by need for more senior people into key ICP positions for training and the fact that although sufficient training was offered, few people attended. | 3.1.2 Continually offer training programs to enhance trained base. | Training
|  |  | 3.3 Don't change teams unless for a good reason | 3.2.1 Review procedures and change training program if necessary | Training
|  | Need to redistribute multi-disciplined CCC volunteers to other posts. | 3.4 To solve the shortage of CERT people times, a method needs to be worked out between groups for reassignment of people qualified in multiple disciplines to reassign them as required by the site IC and not pigeon-hole people into one discipline. | 3.4.1 Senior CCC members from each discipline need to work out a procedure and disseminate to members. | Planning
| 4. EOC Management | Required equipment for DOC not found | 4.1 Procure and store equipment for DOC | 4.1.1 Define requirements | Planning
|  |  |  | 4.1.2 Procure or re-allocate equipment and store in EOC | Equipment
|  |  |  | 4.1.3 Drill for DOC operation, using stored equipment | Exercises
|  | Interaction between EOC and CCC DOC not tested | 4.2 Joint training involving EOC and CCC DOC staff | 4.2.1 Tabletop with key EOC staff and CCC DOC | Exercises
|  | Sit stat information in DOC poor to non existent | 4.3 Implement process which ensures DOC receives appropriate sit stat information | 4.3.1 Train ICP command staff to understand information requirement | Training
|  |  |  | 4.3.2 Implement antenna drop in EOC so that DOC staff can copy CARES traffic | Equipment
|  | Communication and coordination between CCC DOC and ICP slow or no response | 4.4 Training of ICP command staff | 4.4.1 Refresher training for ICP command staff: SEMS, ICS | Training
|  |  |  | 4.4.2 Document CC DOC roles and responsibilities | Planning
|  |  |  | 4.4.3 Train senior CCC staff on DOC roles and responsibilities | Leadership
|  |  |  | 4.4.4 Tabletop exercise with ICP command staff | Leadership
| 5. Volunteer Management | Silos between the CCC branches | 5.1 Better understanding of capabilities across CCC branches | 5.1.1 Workshop with CARES, CERT, DART and MRC leadership | Leadership
|  |  |  | 5.1.2 Additional training for all CCC members | Training
| 6. Search and Rescue |  | 6.1 … | 6.1.1 …
6.1.2 …
| 7. Emergency Public Information and Warning | Information dissemination from EOC and PIO via DOC and ICP to residents not tested | 7.2 Test the capability to send information to the ICP and disseminate via bulletin board | 7.2.1 Clarify responsibilities and message formats | Planning
|  |  |  | 7.2.2 Drill information dissemination from EOC via DOC and ICP to residents | Exercises
| 8. Emergency Triage and Pre-Hospital Treatment |  | 8.1 … | 8.1.1 …
8.1.2 …
| 9. Equipment and Supplies | Trailer needs improvements as it was unlevel and had a flat tire. Also, ramp was slippery with loose dirt and part of load shifted. | 9.1 | 9.1.1 Have leveler jacks and side level indicators on the side and back.
9.1.2 Put in a tire pump and a pressure gauge. (Ken, have the Corp Yard check the tire on the door side for leaks)
9.1.3 Put in a step-by-step instructions for leveling and stabilizing the trailer when parked. Need hooks for loose straps.
9.1.4 Need the ramp and floor of the trailer to be painted with sanded floor enamel to prevent slipping.
9.1.5 Need some packing stretch warp available to tie down opened packages, partially open waters, etc.
|  |  | 9.2 Need to have an easier way to use command post position signs. | 9.2.1 …
Capability definition as per Department of Homeland Security Target Capabilities List (http://www.fema.gov/pdf/government/training/tcl.pdf)